## ورقة1
Team BackLog
Scope | Task Name | Assignee | Task status | Expected Time to finish | Actual time to finish
Coding | Ultra Sonic | Mohamed Sayed | Done | 16 hrs. | 8 hrs.
| Input Capture Unit |  | Done |  | 8 hrs.
| Main_Flow | Moustafa AbdElrahim | Done | 32 hrs. | 35 hrs.
|  | Kareem Magdy | Done
Mohamed Abdullwahab
Nada AbdElazim
|  |  |  | 8 hrs. | 2 hrs.
Documentaion | Test Protcol Sheet | Mohamed Abdullwahab | Done | 2 hrs. | 2 hrs.
|  | Moustafa AbdElrahim |  | 4 hrs. | 4 hrs.
| Design Document | Nada AbdElazim | Done | 4 hrs. | 4 hrs.